{"text_format":"3","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"defined_names":1},"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":222,"n_cols":12,"rows_kept":222,"merged":[[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,3,6],[2,7,2,9],[2,10,3,10],[2,11,3,11]]}
["洪江市2023年巩固脱贫攻坚成果和衔接乡村振兴项目计划完成情况表"]
[]
["序号","计划文件","项目名称","施工单位","计划金额（万元）","是否完工","已报账金额（万元）","其中",null,null,"绩效目标实现情况","联农带农情况"]
[{"$nulls":7},"财政衔接资金","统筹整合资金","其他自筹资金"]
[{"$nulls":4},{"$f":"SUM(E6:E222)","v":17539.15},null,11878.45,11878.45,0,5660.7]
[1,"洪委乡振组[2023]5号","2023年高质量庭院经济以奖代补","洪江市农业农村局",225,"是",225,225,0,0,"完成对发展产业的1500户脱贫户、监测户按照标准开展产业奖补","扶持1500户脱贫户、监测户发展庭院经济增收"]
[2,"洪委乡振组[2023]5号","怀化国家农科园柑橘种苗基地建设项目","黔阳生态农业发展有限公司",200,"是",200,200,0,0,"完成建成60亩试验基地","带动促进产业发展"]
[3,"洪委乡振组[2023]5号","“洪华”系列柑橘新品种试验示范基地建设","洪江市农业科学技术研究所",15,"是",15,15,0,0,"完成柑橘试验基地","带动促进产业发展"]
[4,"洪委乡振组[2023]25号","洪江市高标准农田建设项目","株洲新洲建筑安装有限责任公司\n益阳龙光桥建筑工程有限公司\n湖南省新化县燎星建筑有限公司\n湖南利邦工程建设有限公司\n湖南弘运建筑有限公司\n湖南省娄底市第一工程有限公司\n",{"v":3252,"d":"3252.00"},"是",{"v":669,"d":"669.00"},{"v":669,"d":"669.00"},0,2583,"完成建设高标准农田1.95万亩，受益11600户40600人。","吸纳群众务工增收，改善生产条件，促进产业增收"]
[5,"洪委乡振组[2023]29号","新型经营主体贷款贴息","洪江市农业农村局",{"v":46,"d":"46.00"},"是",{"v":46,"d":"46.00"},{"v":46,"d":"46.00"},0,0,"完成对新型经营主体贷款贴息","带动促进产业发展"]
[6,"洪委乡振组[2023]26号\n","湖南锐乐健康产业有限公司中药材产地加工建设项目","湖南锐乐健康产业有限公司",100,"是",100,100,0,0,"完成设备建设，受益342户1463人","吸纳群众务工，收益分红"]
[7,"洪委乡振组[2023]26号\n","湖南省宝顶生态农业有限公司中药材（枳壳）及冰糖柚产业基地标准化建设项目","湖南省宝顶生态农业有限公司",100,"是",100,100,0,0,"完成成仓储库及基地建设，受益172户403人","吸纳群众务工，收益分红"]
[8,"洪委乡振组[2023]26号\n","洪江市溶溪生态种养专业合作社冰糖柚生产基地设施化建设项目","洪江市溶溪生态种养专业合作社",30,"是",30,30,0,0,"完成基地设施建设，受益416户1100人","吸纳群众务工，收益分红"]
[9,"洪委乡振组[2023]26号\n","洪江市威农果蔬专业合作社仓储设施建设项目","洪江市威农果蔬专业合作社",30,"是",30,30,0,0,"完成仓储库建设一座，受益204户632人","吸纳群众务工，收益分红"]
[10,"洪委乡振组[2023]26号\n","洪江市君惠果业专业合作社柑橘产业基地标准化建设项目","洪江市君惠果业专业合作社",30,"是",30,30,0,0,"完成柑桔基地建设，受益35户124人","吸纳群众务工，收益分红"]
[11,"洪委乡振组[2023]26号\n","洪江市玖盛有机茶叶种植专业合作社茶叶加工建设项目","洪江市玖盛有机茶叶种植专业合作社",20,"是",20,20,0,0,"完成设备建设及冷藏库建设，130户336人","吸纳群众务工，收益分红"]
[12,"洪委乡振组[2023]27号","农产品产地仓储保鲜冷链设施建设补贴项目","湖南绿盾制冷技术有限公司、新化县鑫丰制冷设备科技有限公司、长沙奇华工程管理有限公司",{"v":201,"d":"201.00"},"是",{"v":201,"d":"201.00"},{"v":201,"d":"201.00"},0,0,"完成4个以上农产品冷藏保鲜项目奖补","带动当地群众就业500余人"]
[13,"洪委乡振组[2023]25号","岔头乡繁溪村农村供水保障新建工程","湖南优发建设有限公司",{"v":180,"d":"180.00"},"是",{"v":180,"d":"180.00"},{"v":180,"d":"180.00"},0,0,"完成供水保障工程建设，受益345户1248人","吸纳群众务工，保障饮水"]
[14,"洪委乡振组[2023]25号","大崇乡兰家村农村供水保障新建工程","凯益环境建设集团有限公司",{"v":140,"d":"140.00"},"是",{"v":140,"d":"140.00"},{"v":140,"d":"140.00"},0,0,"完成供水保障工程建设，受益213户849人","吸纳群众务工，保障饮水"]
[15,"洪委乡振组[2023]25号","安江镇秀建村八门片区农村供水保障新建工程","湖南宏成建设工程有限公司",{"v":180,"d":"180.00"},"是",{"v":180,"d":"180.00"},{"v":180,"d":"180.00"},0,0,"完成供水保障工程建设，受益313户977人","吸纳群众务工，保障饮水"]
[16,"洪委乡振组[2023]5号","洪江市雪峰山国有林场2023年欠发达国有林场林下种植产业建设项目","洪江市旺华家庭农场",60,"是",60,60,0,0,"完成天麻种植65亩；完成黄精种植15亩；完成乌骨鸡养殖500羽。","吸纳群众务工"]
[17,"洪委乡振组[2023]5号","洪江市八面山国有林场2023年欠发达国有林场林业产业公路硬化","湖南新佑路桥工程有限公司",{"v":70,"d":"70.00"},"是",40,{"v":40,"d":"40.00"},0,30,"完成产业公路硬化1.7公里","吸纳群众务工"]
[18,"洪委乡振组[2023]27号","洪江市岔头乡鸡公坡村等26个村农村环境综合整治项目","怀化市生态环境局洪江市分局",149.14,"是",149.14,149.14,0,0,"完成污水治理26个村，受益240户860人","吸纳群众务工，改善人居环境"]
[19,"洪委乡振组[2023]5号","2023年小额信贷贴息","洪江市乡村振兴局",262,"是",262,262,0,0,"完成对贷款脱贫人口进行贴息","脱贫人口贷款发展产业增收"]
[20,"洪委乡振组[2023]5号","2023年职业教育补助","洪江市乡村振兴局",{"v":390,"d":"390.00"},"是",{"v":390,"d":"390.00"},{"v":390,"d":"390.00"},0,0,"完成2600人次职业教育补贴","教育补助脱贫人口，提高就业率"]
[21,"洪委乡振组[2023]5号","2023年公益性岗位项目","洪江市乡村振兴局",1142.97,"是",1067.97,1067.97,0,75,"完成1229位公益性岗位人员补贴","公益性岗位人员务工增收"]
[22,"洪委乡振组[2023]5号","2023年创业培训及首厕过关制培训","洪江市乡村振兴局",5,"是",5,5,0,0,"完成创业培训及首厕过关培训","培训发展产业技能"]
[23,"洪委乡振组[2023]5号","2023年项目管理费","洪江市乡村振兴局",39,"是",39,39,0,0,"完成2023年度项目建设","保障项目实施，吸纳群众务工及项目受益"]
[24,"洪委乡振组[2023]12号、29号","洪江市农村公共厕所新建项目","鲍小平、严昌国、胡平、曾纪贤、周福安、杨开光、谢树林等",552.22,"是",297.22,297.22,0,255,"完成公厕建设30座，受益2624户7823人","吸纳群众务工，改善人居环境"]
[25,"洪委乡振组[2023]25号","2023年创业致富带头人培训","湖南商务职业技术学院",{"v":38.8,"d":"38.80"},"是",{"v":38.8,"d":"38.80"},{"v":38.8,"d":"38.80"},0,0,"完成培训任务","致富带头人带动群众发展产业增收"]
[26,"洪委乡振组[2023]29号","省消费帮扶示范中心洪江市馆租金补贴","洪江市乡村振兴局",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成租金补贴","带动农产品销售"]
[27,"洪委乡振组[2023]30号\n","洪江市2023年巩固拓展脱贫攻坚成果示范园区-洪江市黔阳生态农业有限公司产业发展项目","洪江市黔阳生态农业有限公司",{"v":3858.1,"d":"3858.10"},"是",{"v":1511.5,"d":"1511.50"},{"v":1511.5,"d":"1511.50"},0,2346.6,"完成柑橘园500亩、黄精1000亩等建设","吸纳群众务工"]
[28,"洪委乡振组[2023]30号\n","洪江市2023年巩固拓展脱贫攻坚成果示范园区-湖南黔阳雪峰农业发展有限公司柑橘产业发展项目","湖南黔阳雪峰农业发展有限公司",{"v":597,"d":"597.00"},"是",{"v":450,"d":"450.00"},{"v":450,"d":"450.00"},0,147,"完成柑橘加工车间建设等","吸纳群众务工"]
[29,"洪委乡振组[2023]30号\n","洪江市2023年巩固拓展脱贫攻坚成果示范园区-怀化林泉药业有限公司中药材产业发展项目","怀化林泉药业有限公司",{"v":100,"d":"100.00"},"是",{"v":38.5,"d":"38.50"},{"v":38.5,"d":"38.50"},0,61.5,"完成中药材基地600亩及生产线建设","吸纳群众务工"]
[30,"洪委乡振组[2023]29号","洪江市农村卫生厕所改造项目","洪江市乡村振兴局",21.23,"是",21.23,21.23,0,0,"完成厕所改造奖补","吸纳群众务工，改善人居环境"]
[31,"洪委乡振组[2023]36号","洪江市村集体经济委托帮扶项目","镡城山水公司",{"v":1000,"d":"1000.00"},"是",{"v":1000,"d":"1000.00"},{"v":1000,"d":"1000.00"},0,0,"完成30个村集体经济项目","吸纳群众务工，收益分红"]
[32,"洪委乡振组[2023]25号","2022年度就业帮扶车间稳岗补贴项目","洪江市人力资源保障局",38.2,"是",38.2,38.2,0,0,"完成稳岗补贴191人","吸纳群众务工"]
[33,"洪委乡振组[2023]5号","安江镇婆田村仓储建设","洪江市天晟贸易有限公司",30,"是",30,30,0,0,"修建仓库400平方米，受益610户1921人","吸纳群众务工增收，壮大村集体经济"]
[34,"洪委乡振组[2023]5号","安江镇下坪村柑橘产业路提质改造项目","湖南同联建设工程有限公司",200,"是",200,200,0,0,"完成柑橘产业路2200米提质建设，受益1251户4650人","吸纳群众务工增收，改善生产条件促进产业增收"]
[35,"洪委乡振组[2023]5号","安江镇稔禾溪村新建油茶项目","湖南创建渣土运输服务有限责任公司",30.65,"是",20.65,20.65,0,10,"完成油茶100亩，增加村集体收入，受益532户1474人","吸纳群众务工增收，土地流转，壮大村集体经济"]
[36,"洪委乡振组[2023]5号","安江镇大垅村油茶抚育项目","洪江市向姐果业农民专业合作社",15.25,"是",15.25,15.25,0,0,"完成油茶350亩后扶，468户1478人","吸纳群众务工增收，土地流转，壮大村集体经济"]
[37,"洪委乡振组[2023]5号","安江镇高阳村木姜子基地后扶项目","高阳村民委员会",4,"是",4,4,0,0,"完成100亩木姜子抚育，受益63户，受益245人","吸纳群众务工增收，壮大村集体经济"]
[38,"洪委乡振组[2023]25号","安江镇稔禾溪村道路及桥梁附属工程建设","石祖才",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成护坎修建，237户522人","吸纳群众务工增收，改善生产条件促进产业增收"]
[39,"洪委乡振组[2023]29号","安江镇助溪村新建冰糖柚基地项目","胡群",{"v":50,"d":"50.00"},"是",{"v":50,"d":"50.00"},{"v":50,"d":"50.00"},0,0,"完成种植冰糖柚100亩，受益345户1107人","吸纳群众务工增收，土地流转，壮大村集体经济"]
[40,"洪委乡振组[2023]29号","安江镇洪溪村新修楠竹产业路项目","李根生",{"v":24,"d":"24.00"},"是",{"v":24,"d":"24.00"},{"v":24,"d":"24.00"},0,0,"完成新建产业路1.4公里，受益104户247人","吸纳群众务工增收，改善生产条件促进产业增收"]
[41,"洪委乡振组[2023]29号","安江镇高阳村新修柑橘产业路项目","卢建清",{"v":24.3,"d":"24.30"},"是",{"v":24.3,"d":"24.30"},{"v":24.3,"d":"24.30"},0,0,"完成新建产业路1.5公里等建设，受益134户418人","吸纳群众务工增收，改善生产条件促进产业增收"]
[42,"洪委乡振组[2023]29号","安江镇高阳村2组渠道三面防渗项目","蒋宗永",{"v":34.4,"d":"34.40"},"是",{"v":34.4,"d":"34.40"},{"v":34.4,"d":"34.40"},0,0,"完成渠道硬化1760米，受益97户263人","吸纳群众务工增收，改善生产条件促进产业增收"]
[43,"洪委乡振组[2023]29号","安江镇高阳村5组、6组渠道三面防渗项目","洪江市维杰建设工程处",{"v":41.3,"d":"41.30"},"是",{"v":41.3,"d":"41.30"},{"v":41.3,"d":"41.30"},0,0,"完成渠道硬化2540米，受益107户304人","吸纳群众务工增收，改善生产条件促进产业增收"]
[44,"洪委乡振组[2023]29号","安江镇山塘整治奖补项目","唐菊香、蒋新友",{"v":56,"d":"56.00"},"是",{"v":56,"d":"56.00"},{"v":56,"d":"56.00"},0,0,"完成28处山塘增蓄扩容。受益1529户4867人","改善灌溉条件，促进产业增收"]
[45,"洪委乡振组[2023]29号","安江镇高速连接线垃圾治理项目","洪江市中弘建筑工程有限公司",{"v":15.2,"d":"15.20"},"是",{"v":15.2,"d":"15.20"},{"v":15.2,"d":"15.20"},0,0,"完成25个垃圾治理点建设，受益205户672人","吸纳群众务工，改善人居环境"]
[46,"洪委乡振组[2023]27号","安江镇大垅村渠道三面防渗项目","潘继来",10.86,"是",10.86,10.86,0,0,"完成渠道硬化900米，受益49户172人","吸纳群众务工，改善灌溉条件"]
[47,"洪委乡振组[2023]27号","安江镇涝溪村黄桃产业路建设项目","蒋华",{"v":30,"d":"30.00"},"是",{"v":30,"d":"30.00"},{"v":30,"d":"30.00"},0,0,"产业路扩宽及硬化2500平方米，受益135户474人","吸纳群众务工，改善群众生产条件"]
[48,"洪委乡振组[2023]5号","岔头乡大沅村油茶\n抚育项目","大沅村村民委员会",3.2,"是",3.2,3.2,0,0,"完成油茶后扶64亩，受益328户1042人","吸纳群众务工，土地流转，收益分红"]
[49,"洪委乡振组[2023]5号","岔头乡鸡公坡村油茶抚育项目","鸡公坡村村民委员会",3,"是",3,3,0,0,"完成油茶后扶60亩，受益207户575人","吸纳群众务工，土地流转，收益分红"]
[50,"洪委乡振组[2023]5号","岔头乡羊坡村油茶抚育项目","羊坡村村民委员会",2.5,"是",2.5,2.5,0,0,"完成油茶后扶50亩，受益370户1420人","吸纳群众务工，土地流转，收益分红"]
[51,"洪委乡振组[2023]29号","岔头乡陶家村山核桃产业路硬化项目","黄跃华",{"v":49.2,"d":"49.20"},"是",{"v":29.2,"d":"29.20"},{"v":29.2,"d":"29.20"},0,20,"完成产业路硬化1200米，受益107户335人","吸纳群众务工，促进产业增收。"]
[52,"洪委乡振组[2023]29号","岔头乡山塘整治奖补项目","谢树林、段维芳",{"v":32,"d":"32.00"},"是",{"v":32,"d":"32.00"},{"v":32,"d":"32.00"},0,0,"完成山塘治理16处，受益1938户5790人","吸纳群众务工，增加山塘蓄水、灌溉能力。"]
[53,"洪委乡振组[2023]27号","岔头乡提升山上经济作物灌溉水源保障能力奖补项目","贺有良",{"v":4,"d":"4.00"},"是",{"v":4,"d":"4.00"},{"v":4,"d":"4.00"},0,0,"完成山塘治理2处，受益115户396人","吸纳群众务工，增加山塘蓄水、灌溉能力。"]
[54,"洪委乡振组[2023]29号","大崇乡山塘整治奖补项目","段惟林、蒋益贵等",{"v":12,"d":"12.00"},"是",{"v":12,"d":"12.00"},{"v":12,"d":"12.00"},0,0,"完成山塘治理6处，受益302户937人","吸纳群众务工，改善灌溉条件"]
[55,"洪委乡振组[2023]27号","大崇乡提升山上经济作物灌溉水源保障能力奖补项目","蒋生根",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成山塘治理5处，受益479户1594人","吸纳群众务工，改善灌溉条件"]
[56,"洪委乡振组[2023]27号","大崇乡岩脚村渠道三面防渗项目","岩脚村民委员会",{"v":18,"d":"18.00"},"是",{"v":18,"d":"18.00"},{"v":18,"d":"18.00"},0,0,"完成渠道防渗1620米，受益89户301人","吸纳群众务工，改善生产条件"]
[57,"洪委乡振组[2023]35号","江市镇青山园村柑橘基地配套设施建设项目","洪江市腾达生态种植专业合作社",30,"是",30,30,0,0,"完成柑橘基地配套设施建设，受益640户2347人","吸纳群众务工，收益分红"]
[58,"洪委乡振组[2023]5号","江市镇岳溪村、里坪村联建粮油加工厂项目","洪江市鑫禾农机专业合作社",50,"是",50,50,0,0,"完成新建粮油加工厂一座，受益144户348人","吸纳群众务工，收益分红"]
[59,"洪委乡振组[2023]5号","江市镇双龙村枳壳基地后扶项目","湖南宝顶生态农业有限公司",6,"是",6,6,0,0,"完成100亩枳壳基地后续除草、施肥、剪枝，受益400户1410人","吸纳群众务工，收益分红"]
[60,"洪委乡振组[2023]12号","江市镇青山园村改造农村公共厕所项目","胡平",{"v":5,"d":"5.00"},"是",{"v":5,"d":"5.00"},{"v":5,"d":"5.00"},0,0,"完成公厕建设一座，受益640户2347人","吸纳群众务工"]
[61,"洪委乡振组[2023]29号","江市镇红莲洑水村壮大村集体经济项目","黔阳生态农业发展有限公司",{"v":50,"d":"50.00"},"是",{"v":50,"d":"50.00"},{"v":50,"d":"50.00"},0,0,"完成购置2个太空舱入股，受益970户3370人","吸纳群众务工，收益分红"]
[62,"洪委乡振组[2023]29号","江市镇竹滩村水产养殖产业路硬化项目","杨安贵",{"v":12,"d":"12.00"},"是",{"v":12,"d":"12.00"},{"v":12,"d":"12.00"},0,0,"完成产业路建设640平方米，受益47户122人","吸纳群众务工，改善生产条件"]
[63,"洪委乡振组[2023]29号","江市镇红莲洑水村桐油基地产业路硬化","湖南湘云端劳务有限责任公司",{"v":46.5,"d":"46.50"},"是",{"v":46.5,"d":"46.50"},{"v":46.5,"d":"46.50"},0,0,"完成产业路1140米，受益970户3370人","吸纳群众务工，收益分红"]
[64,"洪委乡振组[2023]29号","江市镇双龙村引水渠建设项目","黄玉枚",{"v":10,"d":"10.00"},"是",{"v":7.4,"d":"7.40"},{"v":7.4,"d":"7.40"},0,2.6,"完成新建渠道820米，受益92户184人","吸纳群众务工，改善灌溉条件"]
[65,"洪委乡振组[2023]29号","江市镇双龙村集体经济发展项目","唐刚美",{"v":12.6,"d":"12.60"},"是",{"v":12.6,"d":"12.60"},{"v":12.6,"d":"12.60"},0,0,"完成旧屋改造500平方米，410户1412人","吸纳群众务工"]
[66,"洪委乡振组[2023]29号","江市镇山塘整治奖补项目","杨承刚\n杨安贵\n蒋基平",{"v":30.5,"d":"30.50"},"是",{"v":30.5,"d":"30.50"},{"v":30.5,"d":"30.50"},0,0,"完成12处山塘清淤、维修整治，受益350户1450人","吸纳群众务工"]
[67,"洪委乡振组[2023]29号","江市镇易地搬迁安置点人居环境整治提升项目","洪江市中弘建筑工程有限公司",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成场地硬化180㎡及其他人居环境整治提升工程，受益137户501人","吸纳群众务工，改善人居环境"]
[68,"洪委乡振组[2023]29号","江市镇209国道段垃圾治理项目","湖南湘云端劳务有限责任公司",{"v":21,"d":"21.00"},"是",{"v":21,"d":"21.00"},{"v":21,"d":"21.00"},0,0,"完成新建23个垃圾治理点,开挖污水排水渠500米，受益317户1126人","吸纳群众务工，改善人居环境"]
[69,"洪委乡振组[2023]29号","江市镇岳溪村生态停车场项目","湖南湘云端劳务有限责任公司",{"v":49.5,"d":"49.50"},"是",{"v":49.5,"d":"49.50"},{"v":49.5,"d":"49.50"},0,0,"完成停车场建设一处，受益142户427人","吸纳群众务工"]
[70,"洪委乡振组[2023]29号","江市镇里坪村农村基础建设项目","湖南湘云端劳务有限责任公司",{"v":29.5,"d":"29.50"},"是",{"v":29.5,"d":"29.50"},{"v":29.5,"d":"29.50"},0,0,"完成里坪村通户路碎石垫层、硬化2000平方米，土方回填450立方米，渠道清淤2000米","吸纳群众务工，改善人居环境"]
[71,"洪委乡振组[2023]27号","江市镇江市社区老街巷道硬化项目","杨安贵",{"v":36,"d":"36.00"},"是",{"v":36,"d":"36.00"},{"v":36,"d":"36.00"},0,0,"完成人居环境整治一处，受益133户469人","吸纳群众务工，改善人居环境"]
[72,"洪委乡振组[2023]5号","龙船塘瑶族乡翁朗溪村竹篱笆加工厂项目","蓝栋华",25,"是",25,25,0,0,"完成修建竹篱笆加工厂一座，受益192户670人","带动群众务工，增加村集体经济收入，收益分红"]
[73,"洪委乡振组[2023]15号","龙船塘瑶族乡红心村种养产业灌溉引水项目","洪江市永华建筑队",8,"是",8,8,0,0,"完成水源点至红心村柑橘园和龙口江的引水管安装，受益100户345人","带动群众务工"]
[74,"洪委乡振组[2023]5号","龙船塘瑶族乡翁朗溪村中药材加工厂配套进厂道路硬化项目","蓝栋华",22,"是",22,22,0,0,"完成道路硬化和增设涵管一根，受益190户668人","带动群众务工"]
[75,"洪委乡振组[2023]5号","龙船塘瑶族乡白龙村楠竹产业路提质改造项目","湖南中民项目管理公司",81.3,"是",81.3,81.3,0,0,"完成白龙村一二组连接公路硬化1935米，受益60户380人","带动群众务工，改善生产条件"]
[76,"洪委乡振组[2023]5号","龙船塘瑶族乡光明村油茶抚育项目","龙船塘瑶族乡光明村民委员会",7.95,"是",7.95,7.95,0,0,"完成油茶150亩后扶，221户673人","带动群众务工，土地流转，收益分红"]
[77,"洪委乡振组[2023]5号","龙船塘瑶族乡翁朗溪村人居环境整治提升","洪江市永华建筑队",10,"是",10,10,0,0,"完成修建化粪池一座，受益20户62人","带动群众务工"]
[78,"洪委乡振组[2023]5号","龙船塘瑶族乡翁朗溪村新修机耕桥项目","洪江市永华建筑队",10,"是",10,10,0,0,"完成修建机耕桥一座，受益190户668人","带动群众务工"]
[79,"洪委乡振组[2023]25号","龙船塘瑶族乡翁朗溪村新增生态大米加工生产线","龙船塘瑶族乡翁朗溪村民委员会",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成生态大米加工厂生产线建设，受益221户668人","带动群众务工，增加村集体经济收入，收益分红"]
[80,"洪委乡振组[2023]25号","龙船塘瑶族乡龙船塘社区农村人居环境整治提升项目","洪江市永华建筑队",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成龙船塘社区集镇人居环境改造，受益972户2675人","带动群众务工，改善人居环境"]
[81,"洪委乡振组[2023]29号","龙船塘瑶族乡白龙村新建高山茶叶园项目","龙船塘瑶族乡白龙村民委员会",{"v":50,"d":"50.00"},"是",{"v":50,"d":"50.00"},{"v":50,"d":"50.00"},0,0,"完成新建茶叶园30亩，受益367户1266人","吸纳群众务工，收益分红"]
[82,"洪委乡振组[2023]29号","龙船塘瑶族乡山塘整治奖补项目","洪江市永华建筑队、石青",{"v":4,"d":"4.00"},"是",{"v":4,"d":"4.00"},{"v":4,"d":"4.00"},0,0,"完成山塘维修整治两座，受益104户460人","带动群众务工，改善灌溉条件"]
[83,"洪委乡振组[2023]29号","龙船塘瑶族乡翁朗溪村美丽乡村示范奖补项目","龙船塘瑶族乡翁朗溪村民委员会",{"v":100,"d":"100.00"},"是",{"v":100,"d":"100.00"},{"v":100,"d":"100.00"},0,0,"完成翁朗溪村人居环境改造，受益221户668人","带动群众务工，改善人居环境"]
[84,"洪委乡振组[2023]5号","茅渡乡定坡村柚子产业园项目","鸿安工程劳务有限责任公司",30,"是",30,30,0,0,"完成新建冰糖柚基地100亩，受益119户512人","吸纳群众务工，土地流转，收益分红"]
[85,"洪委乡振组[2023]5号","茅渡乡洒溪村油茶抚育项目","洒溪村村集体经济合作社",3.75,"是",3.75,3.75,0,0,"完成油茶75亩后扶，受益325户1013人","吸纳群众务工，土地流转，收益分红"]
[86,"洪委乡振组[2023]29号","茅渡乡颜容村新建罗汉果基地项目","颜容村民委员会",{"v":50,"d":"50.00"},"是",{"v":50,"d":"50.00"},{"v":50,"d":"50.00"},0,0,"完成种植50亩罗汉果及套种大豆，受益324户683人","吸纳群众务工，土地流转，收益分红"]
[87,"洪委乡振组[2023]29号","茅渡乡光伏电站产业路硬化项目","茅渡乡人民政府",{"v":27.6,"d":"27.60"},"是",{"v":27.6,"d":"27.60"},{"v":27.6,"d":"27.60"},0,0,"完成光伏电站产业路硬化2300㎡，受益112户346人","吸纳群众务工"]
[88,"洪委乡振组[2023]29号","茅渡乡山塘整治奖补项目","唐超",{"v":21,"d":"21.00"},"是",{"v":21,"d":"21.00"},{"v":21,"d":"21.00"},0,0,"完成山塘治理6处，受益440户1653人","吸纳群众务工，改善灌溉条件"]
[89,"洪委乡振组[2023]27号","茅渡乡提升山上经济作物灌溉水源保障能力奖补项目","蒋宗永",{"v":16,"d":"16.00"},"是",{"v":16,"d":"16.00"},{"v":16,"d":"16.00"},0,0,"完成山塘治理7处，受益602户2107人","吸纳群众务工，改善灌溉条件"]
[90,"洪委乡振组[2023]27号","茅渡乡关冲村青山片区、下山连片区应急抗旱水源井工程","洪江市宏昇劳务有限公司",{"v":11,"d":"11.00"},"是",{"v":11,"d":"11.00"},{"v":11,"d":"11.00"},0,0,"完成抗旱水源井建设，受益131户459人","吸纳群众务工，改善灌溉条件"]
[91,"洪委乡振组[2023]5号","黔城镇山门新村山核桃产业路提质改造项目","湖南优发建设有限公司",46,"是",26,26,0,20,"完成核桃产业路1060米提质改造及会车道硬化，受益850户2870人","吸纳群众务工，改善生产生活条件"]
[92,"洪委乡振组[2023]5号","黔城镇桃源村黄桃产业路硬化项目","湖南优发建设有限公司",57.6,"是",57.6,57.6,0,0,"完成桃源村黄桃产业路硬化1600米，受益135户471人","吸纳群众务工，改善生产生活条件"]
[93,"洪委乡振组[2023]5号","黔城镇菊花村油茶产业路建设项目","四川中科振华建筑工程有限司",48,"是",48,48,0,0,"完成菊花村油茶产业路硬化3800㎡，产业路新建700m，受益917户2673人","吸纳群众务工，改善生产生活条件"]
[94,"洪委乡振组[2023]5号","黔城镇双溪口村新建油茶项目","洪江市森辉农林发展专业合作社",91.95,"是",61.95,61.95,0,30,"完成双溪口村新建油茶300亩，受益719户2542人","吸纳群众务工，土地流转，收益分红"]
[95,"洪委乡振组[2023]35号","黔城镇双溪口村新建油茶项目（2期）","洪江市森辉农林发展专业合作社",91.95,"是",61.95,61.95,0,30,"完成双溪口村扩建油茶300亩，受益719户2542人","吸纳群众务工，土地流转，收益分红"]
[96,"洪委乡振组[2023]5号","黔城镇山门新村油茶抚育项目","洪江市向姐果业农民专业合作社",15,"是",15,15,0,0,"完成山门新村炮楼界油茶抚育300亩，受益850户2870人","吸纳群众务工，土地流转，收益分红"]
[97,"洪委乡振组[2023]5号","黔城镇双溪口村油茶抚育项目","双溪口村民委员会",4.05,"是",4.05,4.05,0,0,"完成双溪口村鬼山洞油茶抚育81亩，受益719户2542人","吸纳群众务工，土地流转，收益分红"]
[98,"洪委乡振组[2023]25号","黔城镇莲塘社区（原均田村）供水保障巩固提升项目","洪江市自来水公司",{"v":20,"d":"20.00"},"是",{"v":20,"d":"20.00"},{"v":20,"d":"20.00"},0,0,"完成自来水管网延伸至莲塘社区关溪垅、早禾冲、榨双坪、段景坳四处居民点，自来水入户52户295人","吸纳群众务工，改善饮水条件"]
[99,"洪委乡振组[2023]35号","黔城镇石江村购置农机设备项目","石江村民委员会",{"v":50,"d":"50.00"},"是",{"v":50,"d":"50.00"},{"v":50,"d":"50.00"},0,0,"完成购置联合收割机、旋耕机、油菜联合播种机、轮式拖拉机和无人植保机及附属配套设施","带动群众就业增收，收益分红"]
[100,"洪委乡振组[2023]29号","黔城镇茶溪村柑橘产业路硬化项目","洪江市鑫发源农业科技发展有限公司",{"v":50,"d":"50.00"},"是",{"v":50,"d":"50.00"},{"v":50,"d":"50.00"},0,0,"完成茶溪村8组、13组柑橘产业路硬化1200米","带动群众就业增收，方便群众生产生活"]
[101,"洪委乡振组[2023]29号","黔城镇山塘整治奖补项目","三江村村民委员会等",{"v":72.5,"d":"72.50"},"是",{"v":72.5,"d":"72.50"},{"v":72.5,"d":"72.50"},0,0,"完成贺冲节、斋堂冲等32处山塘清淤、维修整治进行奖补。山平塘奖补标准2万元/处；骨干山塘奖补标准4万元/处。","带动群众就业增收，方便群众生产生活"]
[102,"洪委乡振组[2023]29号","黔城镇双溪社区公厕周边硬化","周爱华",{"v":5.8,"d":"5.80"},"是",{"v":5.8,"d":"5.80"},{"v":5.8,"d":"5.80"},0,0,"完成双溪社区公厕周边硬化486㎡","方便群众生产生活"]
[103,"洪委乡振组[2023]29号","黔城镇长坡村农田改造项目","怀化锋俊工程咨询服务有限公司",{"v":20,"d":"20.00"},"是",{"v":20,"d":"20.00"},{"v":20,"d":"20.00"},0,0,"完成硬化田埂长1500米，宽0.6米；修建机耕道长80米，宽3.5米。","带动群众就业增收，方便群众生产生活"]
[104,"洪委乡振组[2023]29号","黔城镇209国道段垃圾治理项目","湖南湘云端劳务有限责任公司",{"v":49.4,"d":"49.40"},"是",{"v":49.4,"d":"49.40"},{"v":49.4,"d":"49.40"},0,0,"完成209国道沿线新建80个垃圾治理点","带动群众就业增收，方便群众生产生活"]
[105,"洪委乡振组[2023]29号","黔城镇板桥村入户路硬化建设项目","洪江市鑫发源农业科技发展有限公司",29.92,"是",29.92,29.92,0,0,"完成板桥村入户路硬化2065㎡","方便群众生产生活"]
[106,"洪委乡振组[2023]29号","黔城镇江南村入户路硬化建设项目","洪江市鑫发源农业科技发展有限公司",27.78,"是",27.78,27.78,0,0,"完成江南村入户路硬化1844㎡","方便群众生产生活"]
[107,"洪委乡振组[2023]27号","黔城镇提升山上经济作物灌溉水源保障能力奖补项目","邱明",{"v":6,"d":"6.00"},"是",{"v":6,"d":"6.00"},{"v":6,"d":"6.00"},0,0,"完成山塘治理3处，改善灌溉条件","带动群众就业增收，改善灌溉条件"]
[108,"洪委乡振组[2023]27号","黔城镇桃源村黄桃产业路提质改造项目","湖南优发建设有限公司",{"v":30,"d":"30.00"},"是",{"v":30,"d":"30.00"},{"v":30,"d":"30.00"},0,0,"完成2组黄桃产业路扩宽及硬化1400米，砌坎3处","带动群众就业增收，改善生产生活条件"]
[109,"洪委乡振组[2023]5号","群峰乡上洞村油茶园后续培管项目","杨理润",16,"是",16,16,0,0,"完成后续培管油茶300亩，受益251户877人","吸纳群众务工，收益分红"]
[110,"洪委乡振组[2023]5号","群峰乡永胜村油茶抚育项目","陈宗献",8.3,"是",8.3,8.3,0,0,"完成油茶150亩后扶，受益466户1631人","吸纳群众务工，收益分红"]
[111,"洪委乡振组[2023]5号","群峰乡芙蓉溪村油茶抚育项目","永盛油茶合作社",5.25,"是",5.25,5.25,0,0,"完成油茶100亩后扶，受益554户1942人","吸纳群众务工，收益分红"]
[112,"洪委乡振组[2023]5号","群峰乡龙山田村油茶抚育项目","杨锡亮",6.55,"是",6.55,6.55,0,0,"完成油茶200亩后扶，受益312户1094人","吸纳群众务工，收益分红"]
[113,"洪委乡振组[2023]29号","群峰乡山塘整治奖补项目","唐海",{"v":6,"d":"6.00"},"是",{"v":6,"d":"6.00"},{"v":6,"d":"6.00"},0,0,"完成山塘治理3处，受益118户398人","吸纳群众务工"]
[114,"洪委乡振组[2023]29号","群峰乡蛇形村公路硬化及桥梁建设项目","娄底明朝交通工程有限公司",{"v":48.5,"d":"48.50"},"是",{"v":48.5,"d":"48.50"},{"v":48.5,"d":"48.50"},0,0,"完成桥梁及公路硬化建设，受益267户745人","吸纳群众务工，改善生产生活条件"]
[115,"洪委乡振组[2023]29号","群峰乡蛇形村新增供水水源项目","蒋宗勇",{"v":5,"d":"5.00"},"是",{"v":5,"d":"5.00"},{"v":5,"d":"5.00"},0,0,"完成机井建设一口，受益113户375人","吸纳群众务工"]
[116,"洪委乡振组[2023]15号","沙湾乡忠心村柑橘仓储建设","戈先亨",49,"是",49,49,0,0,"完成新建仓储库700平方米，受益732户2387人","吸纳群众务工，收益分红"]
[117,"洪委乡振组[2023]5号","沙湾乡健康村园艺场改造","洪江市安江柚果业专业合作社",30,"是",30,30,0,0,"完成柑橘品改80亩，受益405户1235人","吸纳群众务工，收益分红"]
[118,"洪委乡振组[2023]5号","沙湾乡独田村油茶林后扶项目","独田村村民委员会",7.5,"是",7.5,7.5,0,0,"完成150亩油茶林后扶项目，受益300户1013人","吸纳群众务工，收益分红"]
[119,"洪委乡振组[2023]5号","沙湾乡沙湾社区油茶抚育项目","向杰果业",6,"是",6,6,0,0,"完成油茶120亩后扶，受益45户213人","吸纳群众务工，收益分红"]
[120,"洪委乡振组[2023]5号","沙湾乡沙湾社区冰糖柚基地后扶","向波果业",2.4,"是",2.4,2.4,0,0,"完成冰糖柚40亩后扶，受益45户213人","吸纳群众务工，收益分红"]
[121,"洪委乡振组[2023]25号","沙湾乡沙湾社区道路、排水道维护修缮","蒋志田果业",{"v":5,"d":"5.00"},"是",{"v":5,"d":"5.00"},{"v":5,"d":"5.00"},0,0,"完成道路维修及排水道建设，受益532户1441人","吸纳群众务工，改善环境"]
[122,"洪委乡振组[2023]29号","沙湾乡寨头村改建仓储库项目","跃华建筑",{"v":15,"d":"15.00"},"是",{"v":15,"d":"15.00"},{"v":15,"d":"15.00"},0,0,"完成仓储库建设一座，受益204户684人","吸纳群众务工，收益分红"]
[123,"洪委乡振组[2023]29号","沙湾乡山塘整治奖补项目","唐红军 、唐建 、向开洪、唐学文",{"v":78,"d":"78.00"},"是",{"v":78,"d":"78.00"},{"v":78,"d":"78.00"},0,0,"完成山塘治理34处，受益1267户4726人","吸纳群众务工，改善灌溉条件"]
[124,"洪委乡振组[2023]27号","沙湾乡提升山上经济作物灌溉水源保障能力奖补项目","沙湾社区居民委员会",{"v":2,"d":"2.00"},"是",{"v":2,"d":"2.00"},{"v":2,"d":"2.00"},0,0,"完成山塘治理1处，受益108户311人","吸纳群众务工，改善灌溉条件"]
[125,"洪委乡振组[2023]27号","沙湾乡沙湾社区樱桃溪片区5、10组生活饮用水改造项目","沙湾社区居民委员会",{"v":25,"d":"25.00"},"是",{"v":25,"d":"25.00"},{"v":25,"d":"25.00"},0,0,"完成饮水工程提质，受益116户413人","吸纳群众务工，保障饮水"]
[126,"洪委乡振组[2023]5号","深渡苗族乡浪溪冲村农业大棚项目","湖南湘云端劳务有限责任公司",20,"是",20,20,0,0,"完成大棚建设9.8亩，受益165户625人","吸纳群众务工，收益分红"]
[127,"洪委乡振组[2023]35号","深渡苗族乡深渡村乡村旅游游步道项目","杨天国",20,"是",20,20,0,0,"完成游步道等建设，受益368户1032人","吸纳群众务工"]
[128,"洪委乡振组[2023]15号","深渡苗族乡上坪村壮大村集体经济项目","洪江市玉龙水电有限责任公司",30,"是",30,30,0,0,"完成入股投资30万元，受益349户1071人","吸纳群众务工，收益分红"]
[129,"洪委乡振组[2023]5号","深渡苗族乡合建村油茶抚育项目","杨勇",3.75,"是",3.75,3.75,0,0,"完成油茶75亩后扶，受益372户1110人","吸纳群众务工，收益分红"]
[130,"洪委乡振组[2023]5号","深渡苗族乡牛溪脑村油茶抚育项目","汤立德",4.45,"是",4.45,4.45,0,0,"完成油茶100亩后扶，受益20户56人","吸纳群众务工，收益分红"]
[131,"洪委乡振组[2023]25号","深渡苗族乡花洋溪村农村人居环境整治提升项目","向培彬",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成水渠硬化400米及环境整治，227户573人","吸纳群众务工"]
[132,"洪委乡振组[2023]35号","深渡苗族乡深渡村楠竹产业路硬化项目","袁明华",{"v":20,"d":"20.00"},"是",{"v":20,"d":"20.00"},{"v":20,"d":"20.00"},0,0,"完成楠竹产业路1850平方米建设，受益327户1217人","吸纳群众务工，改善生产条件"]
[133,"洪委乡振组[2023]29号","深渡苗族乡山塘整治奖补项目","吕芳云",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成山塘治理5处，受益162户556人","吸纳群众务工"]
[134,"洪委乡振组[2023]29号","深渡乡花洋溪村供水工程水源改造","花洋溪村村民委员会",{"v":5,"d":"5.00"},"是",{"v":5,"d":"5.00"},{"v":5,"d":"5.00"},0,0,"完成古井改造一处，受益127户420人","吸纳群众务工"]
[135,"洪委乡振组[2023]27号","深渡苗族乡东方红村杉木溪山塘除险加固项目","东方红村村民委员会",{"v":15,"d":"15.00"},"是",{"v":15,"d":"15.00"},{"v":15,"d":"15.00"},0,0,"完成山塘治理1处，受益59户208人","吸纳群众务工，改善灌溉条件"]
[136,"洪委乡振组[2023]5号","熟坪乡尚保村新建木姜子树基地","杨娟",35,"是",35,35,0,0,"完成种植木姜子200亩，受益395户1141人","吸纳群众务工，土地流转，收益分红"]
[137,"洪委乡振组[2023]15号","熟坪乡大湾村杂交水稻制种","杨章元",7,"是",7,7,0,0,"完成水稻制种35亩，受益230户746人","吸纳群众务工，土地流转，收益分红"]
[138,"洪委乡振组[2023]15号","熟坪乡大湾村新建产业路","汪世先",3,"是",3,3,0,0,"完成产业路1200米，受益230户746人","吸纳群众务工，改善生产生活条件"]
[139,"洪委乡振组[2023]5号","熟坪乡下山村杂交水稻制种","向开亮",10,"是",10,10,0,0,"完成水稻制种50亩，受益57户200人","吸纳群众务工，土地流转，收益分红"]
[140,"洪委乡振组[2023]5号","熟坪乡竹坡村杂交水稻制种","杨长永",10,"是",10,10,0,0,"完成水稻制种50亩，受益561户1632人","吸纳群众务工，土地流转，收益分红"]
[141,"洪委乡振组[2023]5号","熟坪乡花园村杂交水稻制种","易延升",10,"是",10,10,0,0,"完成水稻制种50亩，受益320户1156人","吸纳群众务工，土地流转，收益分红"]
[142,"洪委乡振组[2023]5号","熟坪乡罗翁村杂交水稻制种","谢必华",10,"是",10,10,0,0,"完成水稻制种50亩，受益776户2174人","吸纳群众务工，土地流转，收益分红"]
[143,"洪委乡振组[2023]5号","熟坪乡大垅溪村新建油茶项目","湖南创建渣土运输服务有限责任公司",30.65,"是",20.65,20.65,0,10,"完成新建油茶100亩，受益345户1150人","吸纳群众务工，土地流转，收益分红"]
[144,"洪委乡振组[2023]5号","熟坪乡网塘村油茶基地后扶","蒲宏波",5,"是",5,5,0,0,"完成油茶100亩后扶，受益408户1176人","吸纳群众务工，土地流转，收益分红"]
[145,"洪委乡振组[2023]5号","熟坪乡尚保村冰糖柚管护","向开亮",{"v":3.2,"d":"3.20"},"是",{"v":3.2,"d":"3.20"},{"v":3.2,"d":"3.20"},0,0,"完成冰糖柚80亩后扶，受益395户1141人","吸纳群众务工，土地流转，收益分红"]
[146,"洪委乡振组[2023]29号","熟坪乡尚保村新建天然弱碱水生产加工厂项目","尚保村民委员会",{"v":50,"d":"50.00"},"是",{"v":50,"d":"50.00"},{"v":50,"d":"50.00"},0,0,"完成水厂设施建设，受益50户157人","吸纳群众务工，土地流转，收益分红"]
[147,"洪委乡振组[2023]29号","熟坪乡光伏电站产业路硬化项目","段承福",{"v":9.9,"d":"9.90"},"是",{"v":9.9,"d":"9.90"},{"v":9.9,"d":"9.90"},0,0,"完成产业路275米建设，受益845户3500人","吸纳群众务工，改善生产生活条件"]
[148,"洪委乡振组[2023]35号","熟坪乡尚保村新建天然弱碱水生产加工厂项目（追加）","尚保村民委员会",{"v":20,"d":"20.00"},"是",{"v":20,"d":"20.00"},{"v":20,"d":"20.00"},0,0,"完成水厂设施建设，受益50户157人","吸纳群众务工，土地流转，收益分红"]
[149,"洪委乡振组[2023]29号","熟坪乡山塘整治奖补项目","谢发元",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成山塘治理5处，受益80户280人","吸纳群众务工，改善灌溉条件"]
[150,"洪委乡振组[2023]29号","熟坪乡熟坪社区桥梁建设项目","段承福",{"v":25,"d":"25.00"},"是",{"v":25,"d":"25.00"},{"v":25,"d":"25.00"},0,0,"完成桥梁建设一座，受益204户557人","吸纳群众务工"]
[151,"洪委乡振组[2023]29号","熟坪乡易地扶贫搬迁安置点人居环境整治提升工程","段承福",{"v":5,"d":"5.00"},"是",{"v":5,"d":"5.00"},{"v":5,"d":"5.00"},0,0,"完成人居环境改造一处，受益11户35人","吸纳群众务工，改善人居环境"]
[152,"洪委乡振组[2023]5号","太平乡磨回村土狗养殖","张锡军",20,"是",20,20,0,0,"完成养狗场建设及500只狗喂养，受益526户2023人","吸纳群众务工，收益分红"]
[153,"洪委乡振组[2023]5号","太平乡溶溪村新建冰糖柚产业基地","张武",30,"是",30,30,0,0,"完成冰糖柚种植100亩，受益416户1100人","吸纳群众务工，收益分红"]
[154,"洪委乡振组[2023]5号","太平乡溶溪村油茶抚育项目","溶溪村村委会",4.55,"是",4.55,4.55,0,0,"完成油茶91亩后扶，受益416户1100人","吸纳群众务工，收益分红"]
[155,"洪委乡振组[2023]5号","太平乡福兴村油茶抚育项目","福兴村村委会",3.35,"是",3.35,3.35,0,0,"完成油茶67亩后扶，受益581户1860人","吸纳群众务工，收益分红"]
[156,"洪委乡振组[2023]29号","太平乡补顺村新建农家乐项目","黄跃华",{"v":50,"d":"50.00"},"是",{"v":50,"d":"50.00"},{"v":50,"d":"50.00"},0,0,"完成基地设施建设，受益327户1026人","吸纳群众务工，收益分红"]
[157,"洪委乡振组[2023]29号","太平乡补顺村水渠维修项目","杨立立",{"v":20,"d":"20.00"},"是",{"v":20,"d":"20.00"},{"v":20,"d":"20.00"},0,0,"完成渠道维修8公里，受益586户2093人","吸纳群众务工"]
[158,"洪委乡振组[2023]29号","太平乡山塘整治奖补项目","向开雄",{"v":35,"d":"35.00"},"是",{"v":35,"d":"35.00"},{"v":35,"d":"35.00"},0,0,"完成山塘治理15处，改善灌溉条件","吸纳群众务工"]
[159,"洪委乡振组[2023]29号","太平乡易地扶贫搬迁安置点人居环境整治提升项目","张武",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成人居环境改造一处，受益252户621人","吸纳群众务工"]
[160,"洪委乡振组[2023]27号","太平乡提升山上经济作物灌溉水源保障能力奖补项目","福兴村村委会",{"v":8,"d":"8.00"},"是",{"v":8,"d":"8.00"},{"v":8,"d":"8.00"},0,0,"完成山塘治理3处，改善灌溉条件","吸纳群众务工"]
[161,"洪委乡振组[2023]5号","塘湾镇中山村新修高山蔬菜基地产业路项目","肖华",25,"是",25,25,0,0,"完成新修产业路1400米，受益226户720人","吸纳群众务工"]
[162,"洪委乡振组[2023]5号","塘湾镇白羊村油茶抚育项目","肖卫国",7.5,"是",7.5,7.5,0,0,"完成油茶150亩后扶，受益86户252人","吸纳群众务工，收益分红"]
[163,"洪委乡振组[2023]29号","塘湾镇陈家社区新建挡水墙及防洪堤路面硬化项目","肖前美",{"v":49,"d":"49.00"},"是",{"v":49,"d":"49.00"},{"v":49,"d":"49.00"},0,0,"完成挡土墙及防洪堤道路建设，受益207户612人","吸纳群众务工"]
[164,"洪委乡振组[2023]5号","铁山乡凉竹湾村杨梅品改项目","凉竹湾村村集体经济",40,"是",40,40,0,0,"完成冰糖柚种植120亩，受益667户2501人","吸纳群众务工，收益分红"]
[165,"洪委乡振组[2023]29号","铁山乡山塘整治奖补项目","段承军、向明元",{"v":8,"d":"8.00"},"是",{"v":8,"d":"8.00"},{"v":8,"d":"8.00"},0,0,"完成山塘治理4处，受益231户635人","吸纳群众务工，改善灌溉条件"]
[166,"洪委乡振组[2023]29号","铁山乡易地扶贫搬迁安置点配套基础设施建设项目","段秀菊",{"v":17,"d":"17.00"},"是",{"v":17,"d":"17.00"},{"v":17,"d":"17.00"},0,0,"完成人居环境改造一处，受益36户142人","吸纳群众务工"]
[167,"洪委乡振组[2023]29号","托口镇山塘整治奖补项目","石桥、杨柳、阳荆、王家坳村村民委员会",{"v":15,"d":"15.00"},"是",{"v":15,"d":"15.00"},{"v":15,"d":"15.00"},0,0,"完成山塘治理6处，受益313户1133人","吸纳群众务工，改善灌溉条件"]
[168,"洪委乡振组[2023]35号","托口镇阳岫村青秋脐橙基地产业路铺砂项目","阳岫村村集体经济合作社",{"v":15,"d":"15.00"},"是",{"v":15,"d":"15.00"},{"v":15,"d":"15.00"},0,0,"完成产业路铺砂2.2公里，受益145户327人","吸纳群众务工，改善生产条件"]
[169,"洪委乡振组[2023]27号","托口镇豹雾村楠竹产业路硬化项目","李作华",{"v":29,"d":"29.00"},"是",{"v":29,"d":"29.00"},{"v":29,"d":"29.00"},0,0,"完成产业路硬化760米及错车道建设，受益40户128人","吸纳群众务工"]
[170,"洪委乡振组[2023]5号","湾溪乡堙上村油茶抚育项目","堙上村民委员会",10,"是",10,10,0,0,"完成油茶200亩后扶，受益430户，1226人","吸纳群众务工增收，收益分红"]
[171,"洪委乡振组[2023]5号","湾溪乡云峰村油茶抚育项目","杨子友",14.25,"是",14.25,14.25,0,0,"完成油茶285亩后扶，受益550户，1700人","吸纳群众务工增收，收益分红"]
[172,"洪委乡振组[2023]29号","湾溪乡蒿菜坪村中药材产业路硬化项目","石纪宣",{"v":49.2,"d":"49.20"},"是",{"v":49.2,"d":"49.20"},{"v":49.2,"d":"49.20"},0,0,"完成产业路硬化4100㎡，受益127户406人","吸纳群众务工增收，改善生产条件，促进产业增收"]
[173,"洪委乡振组[2023]29号","湾溪乡堙上村渠道建设项目","堙上村民委员会",{"v":20,"d":"20.00"},"是",{"v":20,"d":"20.00"},{"v":20,"d":"20.00"},0,0,"完成渠道防渗1600米，受益137户322人","吸纳群众务工增收，改善灌溉条件"]
[174,"洪委乡振组[2023]35号","湾溪乡易地扶贫搬迁点配套基础设施建设项目","杨修银",{"v":8,"d":"8.00"},"是",{"v":8,"d":"8.00"},{"v":8,"d":"8.00"},0,0,"完成人居环境改造一处，受益26户82人","吸纳群众务工增收"]
[175,"洪委乡振组[2023]27号","湾溪乡花树脚村油茶产业路硬化","花树脚村民委员会",{"v":42,"d":"42.00"},"是",{"v":42,"d":"42.00"},{"v":42,"d":"42.00"},0,0,"完成产业路硬化1000米建设，受益94户329人","吸纳群众务工增收，改善生产条件，促进产业增收"]
[176,"洪委乡振组[2023]5号","洗马乡洗马潭村油茶抚育项目","洗马潭村民委员会",4.5,"是",4.5,4.5,0,0,"完成油茶90亩后扶，受益308户1354人","吸纳群众务工，收益分红"]
[177,"洪委乡振组[2023]5号","洗马乡老树溪村油茶抚育项目","老树溪村民委员会",{"v":4.9,"d":"4.90"},"是",{"v":4.9,"d":"4.90"},{"v":4.9,"d":"4.90"},0,0,"完成油茶98亩后扶，受益480户1703人","吸纳群众务工，收益分红"]
[178,"洪委乡振组[2023]5号","洗马乡三角溪村油茶植项目","三角溪村民委员会",4.6,"是",4.6,4.6,0,0,"完成油茶92亩后扶，受益376户1008人","吸纳群众务工，收益分红"]
[179,"洪委乡振组[2023]5号","洗马乡古楼坪村油茶抚育项目","古楼坪村民委员会",4.95,"是",4.95,4.95,0,0,"完成油茶99亩后扶，受益523户1593人","吸纳群众务工，收益分红"]
[180,"洪委乡振组[2023]35号","洗马乡洗马潭村村容村貌提升工程","洗马潭村民委员会",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成停车场等建设，受益46户137人","吸纳群众务工"]
[181,"洪委乡振组[2023]29号","洗马乡稠树脚村脆柿种植基地配套设施项目","稠树脚村集体经济合作社",{"v":15,"d":"15.00"},"是",{"v":15,"d":"15.00"},{"v":15,"d":"15.00"},0,0,"完成管理用房建设，受益128户364人","吸纳群众务工"]
[182,"洪委乡振组[2023]29号","洗马乡山塘整治奖补项目","易建业",{"v":6,"d":"6.00"},"是",{"v":6,"d":"6.00"},{"v":6,"d":"6.00"},0,0,"完成山塘治理3处，受益410户1483人","吸纳群众务工，改善灌溉条件"]
[183,"洪委乡振组[2023]29号","洗马乡古楼坪村新修机耕道项目","易中格",{"v":20,"d":"20.00"},"是",{"v":20,"d":"20.00"},{"v":20,"d":"20.00"},0,0,"完成机耕道建设300米及其他设施建设，受益97户261人","吸纳群众务工"]
[184,"洪委乡振组[2023]27号","洗马乡岩背后村中药材产业路硬化项目","易立中",{"v":20,"d":"20.00"},"是",{"v":20,"d":"20.00"},{"v":20,"d":"20.00"},0,0,"完成产业路1670平方米建设，受益118户413人","吸纳群众务工"]
[185,"洪委乡振组[2023]5号","雪峰镇龙家田村新建100亩冰糖柚产业园","易永忠",30,"是",30,30,0,0,"完成冰糖柚种植100亩，受益320户1060人","吸纳群众务工，土地流转，收益分红"]
[186,"洪委乡振组[2023]5号","雪峰镇先锋溪村新建冰糖柚种植基地","唐海",24,"是",24,24,0,0,"完成冰糖柚种植60亩及产业路建设，527户1619人","吸纳群众务工，土地流转，收益分红"]
[187,"洪委乡振组[2023]5号","雪峰镇两溪口村新建冰糖柚基地100亩","卢明钢",30,"是",30,30,0,0,"完成冰糖柚种植100亩，受益140户426人","吸纳群众务工，土地流转，收益分红"]
[188,"洪委乡振组[2023]5号","雪峰镇兰溪冲村120亩冰糖柚种植","唐冬青",41.78,"是",41.78,41.78,0,0,"完成冰糖柚种植120亩，受益585户1807人","吸纳群众务工，土地流转，收益分红"]
[189,"洪委乡振组[2023]5号","雪峰镇永红村新建油茶项目","雪峰镇永红村村民委员会",{"v":122.6,"d":"122.60"},"是",{"v":82.6,"d":"82.60"},{"v":82.6,"d":"82.60"},0,40,"完成油茶种植400亩，受益377户1213人","吸纳群众务工，土地流转，收益分红"]
[190,"洪委乡振组[2023]5号","雪峰镇公坪村油茶基地后扶","杨夕金",5,"是",5,5,0,0,"完成油茶100亩后扶，受益256户780人","吸纳群众务工，土地流转，收益分红"]
[191,"洪委乡振组[2023]5号","雪峰镇永红村油茶基地后扶","雪峰镇永红村村民委员会",9.8,"是",9.8,9.8,0,0,"完成油茶196亩后扶，受益377户1213人","吸纳群众务工，土地流转，收益分红"]
[192,"洪委乡振组[2023]5号","雪峰镇兰溪冲村油茶基地后扶","唐冬青",6.45,"是",6.45,6.45,0,0,"完成油茶129亩后扶，受益585户1807人","吸纳群众务工，土地流转，收益分红"]
[193,"洪委乡振组[2023]5号","雪峰镇界脚村油茶抚育项目","杨夕金",7.75,"是",7.75,7.75,0,0,"完成油茶150亩后扶，受益42户150人","吸纳群众务工，土地流转，收益分红"]
[194,"洪委乡振组[2023]5号","雪峰镇母溪村油茶抚育项目","杨夕金",5.05,"是",5.05,5.05,0,0,"完成油茶100亩后扶，受益366户1177人","吸纳群众务工，土地流转，收益分红"]
[195,"洪委乡振组[2023]5号","雪峰镇先锋溪村油茶抚育项目","易富生",6.3,"是",6.3,6.3,0,0,"完成油茶125亩后扶，受益527户1619人","吸纳群众务工，土地流转，收益分红"]
[196,"洪委乡振组[2023]5号","雪峰镇深渡江村油茶基地后扶","向孙宏",4,"是",4,4,0,0,"完成油茶80亩后扶，受益428户1482人","吸纳群众务工，土地流转，收益分红"]
[197,"洪委乡振组[2023]5号","雪峰镇两溪口村冰糖柚后续扶持","李延生",3.5,"是",3.5,3.5,0,0,"完成冰糖柚50亩后扶，受益76户239人","吸纳群众务工，土地流转，收益分红"]
[198,"洪委乡振组[2023]29号","雪峰镇先锋溪村新建冰糖柚基地项目","唐海",{"v":50,"d":"50.00"},"是",{"v":50,"d":"50.00"},{"v":50,"d":"50.00"},0,0,"完成冰糖柚种植80亩，受益224户673人","吸纳群众务工，土地流转，收益分红"]
[199,"洪委乡振组[2023]29号","雪峰镇山塘整治奖补项目","向会生、易延生、唐守根",{"v":8,"d":"8.00"},"是",{"v":8,"d":"8.00"},{"v":8,"d":"8.00"},0,0,"完成山塘治理4处，受益1775户5537人","吸纳群众务工，改善灌溉条件"]
[200,"洪委乡振组[2023]27号","雪峰镇车力溪村白岩垅、牛塘界集中供水工程","刘开文",{"v":9,"d":"9.00"},"是",{"v":9,"d":"9.00"},{"v":9,"d":"9.00"},0,0,"完成供水设施建设，受益93户328人","吸纳群众务工，保障饮水"]
[201,"洪委乡振组[2023]15号","岩垅乡江坵村新建仓储库","钦永庚",40,"是",40,40,0,0,"完成仓储库建设一座，受益315户1100人","吸纳群众务工，收益分红"]
[202,"洪委乡振组[2023]5号","岩垅乡芦荻坪村蓝莓产业路提质改造项目","钦陈波",24,"是",24,24,0,0,"完成产业路铺砂3公里，受益860户3420人","吸纳群众务工，改善生产条件"]
[203,"洪委乡振组[2023]29号","岩垅乡山塘整治奖补项目","洪江市鸿达工程服务部、洪江市永华建筑\n洪江市岩垅乡坤华建筑、洪江市岩垅乡桂桂建筑队、岩垅乡王安工程队、洪江市忠诚服务劳务队、岩垅乡田连云工程队、洪江市岩垅乡跃华建筑",{"v":51,"d":"51.00"},"是",{"v":51,"d":"51.00"},{"v":51,"d":"51.00"},0,0,"完成山塘治理23处，受益412户1512人","吸纳群众务工，改善灌溉条件"]
[204,"洪委乡振组[2023]27号","岩垅乡提升山上经济作物灌溉水源保障能力奖补项目","洪江市岩垅乡松青工程队、洪江市鸿达工程服务部、洪江市岩垅乡坤华建筑、蒋玉军、洪江市岩垅乡桂桂建筑队\n",{"v":24,"d":"24.00"},"是",{"v":24,"d":"24.00"},{"v":24,"d":"24.00"},0,0,"完成山塘治理9处，受益412户1512人","吸纳群众务工，改善灌溉条件"]
[205,"洪委乡振组[2023]27号","岩垅乡芦荻坪村柑橘产业路建设项目","芦荻坪村民委员会",{"v":25,"d":"25.00"},"是",{"v":25,"d":"25.00"},{"v":25,"d":"25.00"},0,0,"完成产业路硬化2100平方米，受益66户232人","吸纳群众务工，改善生产条件"]
[206,"洪委乡振组[2023]27号","岩垅乡空田村黄桃产业路建设项目","洪江市鑫发源农业科技发展有限公司",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,0,"完成产业路扩建及铺砂1000米建设，受益43户150人","吸纳群众务工，改善生产条件"]
[207,"洪委乡振组[2023]5号","沅河镇富团村村集体经济产业园后扶","富团村集体经济合作社",{"v":2,"d":"2.00"},"是",{"v":2,"d":"2.00"},{"v":2,"d":"2.00"},0,{"$f":"SUM(J213:J223)","v":0},"完成脐橙30亩产业后扶，受益748户2340人","吸纳群众务工，收益分红"]
[208,"洪委乡振组[2023]29号","沅河镇十里村壮大村集体经济项目","黔阳生态农业发展有限公司",{"v":50,"d":"50.00"},"是",{"v":50,"d":"50.00"},{"v":50,"d":"50.00"},0,{"$f":"SUM(J214:J223)","v":0},"完成集体经济门店建设4间，受益421户1322人","吸纳群众务工，收益分红"]
[209,"洪委乡振组[2023]29号","沅河镇沅城村生姜加工厂配套设施建设","黔阳生态农业发展有限公司",{"v":32,"d":"32.00"},"是",{"v":32,"d":"32.00"},{"v":32,"d":"32.00"},0,{"$f":"SUM(J215:J223)","v":0},"完成生姜加工厂建设，受益544户1361人","吸纳群众务工，收益分红"]
[210,"洪委乡振组[2023]29号","沅河镇沅河村7组柑橘产业路建设项目","王立兴",{"v":11,"d":"11.00"},"是",{"v":11,"d":"11.00"},{"v":11,"d":"11.00"},0,{"$f":"SUM(J216:J223)","v":0},"完成产业路150米等建设，受益65户233人","吸纳群众务工，改善生产条件"]
[211,"洪委乡振组[2023]29号","沅河镇富团村产业路硬化","朱春华",{"v":20,"d":"20.00"},"是",{"v":20,"d":"20.00"},{"v":20,"d":"20.00"},0,{"$f":"SUM(J217:J223)","v":0},"完成产业路硬化700米，受益47户128人","吸纳群众务工，改善生产条件"]
[212,"洪委乡振组[2023]29号","沅河镇山塘整治奖补项目","李造、唐存万等",{"v":45,"d":"45.00"},"是",{"v":45,"d":"45.00"},{"v":45,"d":"45.00"},0,{"$f":"SUM(J218:J223)","v":0},"完成山塘治理21处，受益1358户4790人","吸纳群众务工，改善灌溉条件"]
[213,"洪委乡振组[2023]29号","沅河镇清水青村农村供水工程提质改造","清水青村民委员会",{"v":10,"d":"10.00"},"是",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},0,{"$f":"SUM(J219:J223)","v":0},"完成管网延伸建设，受益31户114人","吸纳群众务工，改善饮水条件"]
[214,"洪委乡振组[2023]35号","沅河镇沅城村生态停车场提质改造建设","唐军",{"v":45,"d":"45.00"},"是",{"v":45,"d":"45.00"},{"v":45,"d":"45.00"},0,{"$f":"SUM(J220:J223)","v":0},"完成停车场建设，受益544户1361人","吸纳群众务工"]
[215,"洪委乡振组[2023]29号","沅河镇沅城村风貌提升护坡建设项目","沅城村集体经济股份合作社",{"v":23,"d":"23.00"},"是",{"v":23,"d":"23.00"},{"v":23,"d":"23.00"},0,{"$f":"SUM(J221:J223)","v":0},"完成护坡建设530米，544户1361人","吸纳群众务工"]
[216,"洪委乡振组[2023]27号","沅河镇提升山上经济作物灌溉水源保障能力奖补项目","李造、黄建华等",{"v":22,"d":"22.00"},"是",{"v":22,"d":"22.00"},{"v":22,"d":"22.00"},0,{"$f":"SUM(J222:J223)","v":0},"9处山塘进行了清淤和维修。吸纳脱贫户及监测户及群众务工，促进产业增收","带动监测对象及脱贫人口务工7人，人均增收400元"]
[217,"洪委乡振组[2023]27号","沅河镇沅河村柑橘产业路硬化项目","洪江市志勇建筑有限责任公司",{"v":20,"d":"20.00"},"是",{"v":20,"d":"20.00"},{"v":20,"d":"20.00"},0,{"$f":"SUM(J223:J223)","v":0},"硬化产业路1670平方米。吸纳脱贫户及监测户及群众务工，促进产业增收","带动监测对象及脱贫人口务工3人，人均增收1000元"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0}